## Initial Plan
Initial Plan |  |  |  | Availability | W.B.S. Codes
Resource | Classification | $ per hr | O/T |  | 1.1 | 1.2 | 2.1 | 2.2 | 3.1 | 3.2.1 | 3.2.2 | 3.2.3 | 4.1 | 4.2 | 4.3 | 5.1 | 5.2 | 6.1 | 6.2 | 6.3 | 7 | Cost
Fred | Analyst 3 | 80 | 160 |  | 12 | 48 | 40 | [14 empty] | 8000
John | Analyst 2 | 60 | 120 |  |  |  | 100 |  |  | 48 | [11 empty] | 8880
Mary | Analyst 1 | 40 | 80 | April only | [6 empty] | 48 |  | 40 | [8 empty] | 3520
Peter | Analyst 1 | 40 | 80 | April only | [7 empty] | 48 |  | 40 | 40 |  |  | 40 |  |  |  | 6720
Jenny | Analyst 1 | 40 | 80 | [15 empty] | 40 | 40 | 32 | 4480
Paul | Tech Analyst 3 | 80 | 160 |  |  |  |  | 10 | [13 empty] | 800
Geoff | Tech Analyst 1 | 60 | 120 | [5 empty] | 20 | [12 empty] | 1200
Roy | Technician | 25 | 50 | June+ | [11 empty] | 20 | 20 |  |  |  |  | 1000
Sue | Programmer | 25 | 50 | [9 empty] | 260 |  |  |  |  | 136 |  |  |  | 9900
James | Programmer | 25 | 50 | [10 empty] | 200 |  |  |  |  | 136 |  | 32 | 9200
Tracy | Programmer | 25 | 50 | N/A in June | [10 empty] | 200 |  |  |  |  | 136 |  | 8400
Cont. Analyst | Analyst 1 | [20 empty] | 0
Cont. Prog. | Programmer | [20 empty] | 0
62100

## Activity List
| Activity | Duration | Predecessor
A | Problem Definition | 12
B | Feasibility Study | 48 | A
C | System Analysis | 100 | B
D | Technical Analysis | 10 | B
E | Technical Design | 20 | D
F | System Design - Enrol. | 48 | C
G | System Design - Report. | 48 | C
H | System Design - Assess. | 48 | C
I | Sys Prog. - Enrol. | 260 | F
J | Sys Prog. - Assess. | 200 | G
K | Sys Prog. - Results Report. | 200 | H
L | Hardware implementation | 30 | E
M | Software implementation | 10 | I, J, K, L
N | Enrol. System Test | 136 | M
O | Assess. System Test | 136 | M
P | Results Report. SysTest | 136 | M
Q | User Training | 32 | N, O, P